## foo-page-10-table-1
Auction(2021) timetable | Jan-Mar 2021
Issue of Notice Inviting Applications (NIA) | 6th Jan, 2021
Pre-bid Conference | 12th Jan, 2021
Last date for seeking clarifications on NIA | 15th Jan, 2021
Clarifications to NIA | 28th Jan, 2021
Last date for submission of Applications | 5th Feb, 2021
Publication of Ownership details of Applicants | 12th Feb, 2021
Bidder Ownership Compliance Certificate | 15th Feb, 2021
Pre-qualification of Bidders | 19th Feb,2021
Last date of withdrawal of applications | 22nd Feb, 2021
Final List of bidders | 24th Feb,2021
Mock Auction | 26th Feb, 2021
Start of the Auction | 1st March,2021
Payment of the Successful Bid Amount | Within 10 calendar days of the issue of demand note
Venue and Date/ time of Pre-Bid meeting | Will be notified on DoT website separately